AL LAITH SITE SERVICES · Workshop Stock Control · A3 Executive One-Pager

COEEx OS · 26 May 2026 · Owner Calo · Sponsor Vincent Nibbering · Sign-off John Maddern

| 1 · BACKGROUND 500+ rental assets (cabins, ablutions, golf buggies, utility vehicles, flatpacks). Workshop store has no transactional record, no worker-facing tool, no ERP automation. 30–45 min nightly manual ERP batch (Calo) on days with 20+ issuances. Single SC (Calo) — no backup; weekend cover undecided. 10–12 wk AppSheet build planned (DX Team). Pre-launch programme (A–F) in flight. | 2 · CURRENT CONDITION 100% of parts issued without digital record (PRD §17). 0% ERP auto-update; 30–45 min daily manual batch. 0% low-stock prevention (no monitoring exists). Stock Controller utilisation unknown — model predicts 0.67 at 30 req/d, unstable above 32 req/d. Q1 (ERP integration approach) UNRESOLVED — blocking DX build start. Phase A 45% · Phase B 35% · Phase C 20% · App Build 0% · Labeling 30%. |
| --- | --- |
| 3 · TARGET CONDITION (Go-live + 14d) 100% issues logged with worker / asset / job / timestamp. ≥99.5% ERP sync; <60 sec sync latency. 100% reorder alerts ahead of stockouts. Median cycle time ≤30 min · P95 ≤60 min. Inventory accuracy ≥95% at first monthly count. Cross-trained backup-SC handling ≥1 shift/wk. 14-point time-and-motion telemetry live (zero worker friction). | 4 · ANALYSIS — Root causes (5-Whys + Fishbone) RC-1 · No closed-loop transaction system — historic culture; no one owned a worker-facing layer. RC-2 · Worker ↔ ERP UX gap — e-Resource is an accounting tool, never adapted for the yard. RC-3 · Single Stock Controller bottleneck — backup deferred to go-live; pull it forward. Top waste (TIMWOODS Pareto): Phantom Inventory · Worker Waiting · Worker Transport · Manual ERP Overprocessing. |
| 5 · COUNTERMEASURES (top 5 by Leverage × Feasibility × TTV) R1 · Force Q1 (ERP integration) decision NOW — Sponsor: Vincent. R3 · Embed 14-point time-and-motion telemetry in AppSheet (zero worker overhead; free measurement). R4 · Two-person verify on every catalog item code before import (Calo + Thakur). R14 · Lock category → ERP section mapping (Buggy Parts vs SS Workshop Store) — Calo + IT. R2 · Provision backup-SC role + cross-train one person (Ops Lead). Supporting: 5-min ERP sync watchdog + SMS · catalog synonyms + 'Show all' · batch photography (1 day = 100 items) · stockout AED-impact capture · returns photo-evidence above AED threshold. | 6 · PLAN — 14-week timeline W0 · Q1 decision meeting (60 min). Backup-SC role defined. Inspector calibration day. W1–2 · Batch photography (1 day = 100 items). Phase C catalog crash priority. W2–10 · DX build runs parallel with Phase C. Two-person item-code verify. W10 · UAT (scripted by Calo): stress 100 req/d, watchdog, offline queue, SMS escalation. W11 · Phase F final stock take + TM-14 baseline (30 manually-timed issuances). W12 · Go-live + 2-wk parallel run. Backup-SC covers 1 shift. W14 · Hard-stop ceremony — SC's ERP write access removed; manual batch dead. W16 · 30-day review · TM-14 pre-vs-post A/B published to Vincent + John. |
| 7 · MEASUREMENT (16 KPIs, RAG) Operational scorecard in Workshop_Stock_FullSystem_Diagnostic.xlsx (KPI sheet). Daily: queue, ERP sync, KPI scan. Weekly: scorecard review, P95 RCA, low-stock audit, returns spot-audit, wins broadcast. Monthly: full stock count, FMEA review. Quarterly: catalog hygiene, SOP review. Annual: capacity model refresh, control plan review. | 8 · FOLLOW-UP / RISKS Top 5 RPN (FMEA): Worker non-adoption · SC SPOF · ERP sync silent fail · Q1 unresolved · catalog item-code errors. Each carries a named owner, success metric, and reaction plan in the FMEA sheet. Hard-stop at W14: avoids parallel-system drift. 30-day review (W16) reopens the FMEA + KPI baseline. Companion files: Diagnostic.xlsx · Process_Maps.html · Diagnostic_Report.docx |