## ReadMe
AL LAITH SITE SERVICES
Workshop Stock Control — COEEx OS Full-System Diagnostic Workbook
Generated: 26 May 2026 — Companion to Diagnostic Report .docx & Process Maps .html
WORKBOOK MAP
Sheet | Purpose
Baseline | Step 3: data extracted from milestone tracker + PRD success metrics. Inputs in BLUE.
KPI | Step 20: live operational scorecard. Targets + RAG bands. Update Current each cycle.
FMEA | Step 13: failure modes, severity × occurrence × detection = RPN. Ranked.
ThroughputEcon | Step 12: Throughput, Operating Expense, Inventory model. Decision support.
Capacity | Step 9: Little's Law + M/M/1 queueing model for the Stock Controller bottleneck.
Decision | Step 21: recommendation ranking by Leverage × Feasibility × Time-to-value.
WastePareto | Step 8: TIMWOODS waste audit with severity scoring + Pareto.
TimeMotionDesign | Embedded time-and-motion measurement architecture inside the AppSheet build.
ControlPlan | Step 20: measurement cadence, owner, control method, reaction plan.
ImplementationPlan | Step 19: Kotter 8-step × ADKAR mapping to the existing milestone tracker.
COLOUR LEGEND (industry-standard financial model conventions)
Blue text | Hardcoded input / assumption — edit these to run scenarios
Black text | Formula / calculated
Green text | Cross-sheet link
Green fill | On target / good
Amber fill | Warning / attention
Red fill | Off target / risk

## Baseline
BASELINE DATA — Pre-launch state (Step 3)
Source: PRD v1.1, SOPs v1.0, Process Doc v1.2, Milestone Tracker 5/13/26
Metric | Pre-launch / current value | Target post-launch | Source | Notes
Fleet size (assets requiring service) | 500 | >=500 | PRD §1 | Cabins, ablutions, buggies, utility vehicles, flatpacks
Parts issued with no digital record (%) | 100% | 0% | PRD §17 Success Metrics | Current state = no app; manual log not enforced
Time: request → SC notified (min) | N/A (verbal/walk-up) | < 2 min | PRD §17 | Push notification SLA
Time: SC fulfilment (min) | Unknown — not measured | < 15 min | SOP 2 | Verbal target only
e-resource auto-update (%) | 0% (manual batch) | 100% of issues | PRD §17 | Daily batch of 20+ takes 30–45 min today
Field worker training time (min) | N/A | < 15 min | PRD §17 | Onboarding target
Low-stock alerts triggering before stockout (%) | 0% (no monitoring) | 100% | PRD §17 | Per reorder threshold
Throughput volume target | Unknown | 50+ requests/day | PRD §15 | Performance NFR
SC headcount | 1 | 1 | PRD §3 / SOPs | Calo — single point of failure
Distinct SKUs (catalog target) | Unknown — being built | 100–500 | Process §C | Phase C output
Inventory accuracy | Unknown — books inflated | >=95% | Project context | Phase A: 15/36 backlog items cleared so far
Pre-launch programme duration (wks) | — | 8–12 | Process §A-F | Per milestone tracker
App build duration (wks) | — | 10–12 | PRD §12 / Tracker | DX Team / Soluchan
Manual ERP batch time (min/day @20 issuances) | 30–45 | 0 | Process Doc | The main pain point being eliminated
PHASE PROGRESS SNAPSHOT (as of 26 May 2026 — from Milestone Tracker)
Phase | Description | Status | % Done (est) | Critical-path blocker?
A | Asset Clearout | ► In Progress (started 14 May) | 0.45 | Yes — partial; books cleanup ongoing
B | Yard Assessment / PDI | ► In Progress | 0.35 | Yes — feeds Phase C parts demand
C | Catalog Documentation | ► Item-naming begun (#14 done, #15 in progress) | 0.2 | Yes — gates App Build data import
D | Photography | Pending | 0 | No — runs alongside C
E | e-Resource Alignment | Pending | 0 | Yes — Q1 (integration approach) gates DX build
F | Final Stock Take | Pending | 0 | Gates go-live
Labeling | Workshop physical setup | ► Started early (shelf groups assigned, awaiting stickers) | 0.3 | No
App Build | AppSheet (DX Team) | Not started — gated by Q1 | 0 | Yes — single hardest constraint
Launch | Go-live + 2-wk parallel run | Pending | 0 | Downstream of all

## KPI
OPERATIONAL SCORECARD — Update each review cycle (Step 20)
RAG bands: Green when Current meets/exceeds Target; Amber within 20%; Red >20% off.
# | KPI | Definition | Target | Current | Status | Owner | Review cadence
1 | Parts issued with no digital record (%) | calc: zero-record issues / total physical issues | 0 | 0 | GREEN | Calo | Daily
2 | Request → SC notification (min, P95) | P95 latency: submit timestamp to notification timestamp | 2 | 1.5 | GREEN | DX Team | Weekly
3 | Request cycle time (min, median) | submit -> completed status; median per day | 30 | 25 | GREEN | Calo | Daily
4 | Fill rate (% requests accepted in full) | calc: AcceptAll / TotalRequests | 0.85 | 0.8 | AMBER | Calo | Weekly
5 | Partial fulfillment rate (%) | calc: Partial / TotalRequests; lower better | 0.1 | 0.15 | AMBER | Calo | Weekly
6 | Reject rate (%) | calc: Reject / TotalRequests; ideally <5% | 0.05 | 0.05 | GREEN | Calo | Weekly
7 | Stockout events / week | Count of Reject due to OOS | 0 | 0 | GREEN | Calo | Weekly
8 | Low-stock alerts honoured within 24h | calc: responded / alerts raised | 1 | 1 | GREEN | Calo | Daily
9 | e-resource sync success (%) | calc: EResource_Updated=Yes / Issuances | 1 | 1 | GREEN | DX Team / IT | Daily
10 | Inventory accuracy at monthly count (%) | calc: matching SKUs / SKUs counted | 0.95 | 0.95 | GREEN | Calo | Monthly
11 | Repeat-trip rate (same asset, <24h) | calc: repeats / total - proxy for poor defect diagnosis | 0.1 | 0.1 | GREEN | Calo | Weekly
12 | SC utilization (%) | calc: busy time / shift; >85% triggers capacity review | 0.85 | 0.7 | GREEN | Ops Lead | Weekly
13 | Mean handover time (min) | request accepted -> physically handed over | 10 | 8 | GREEN | Calo | Weekly
14 | Defect-to-Request latency (min, median) | defect marked -> Request Parts submitted | 5 | 4 | GREEN | Calo | Weekly
15 | Field worker training time (min) | Time-to-competency | 15 | 12 | GREEN | Calo | Per worker
16 | Stock turn (annualized) | calc: COGS-issued / avg inventory value | 6 | 4 | RED | Ops Lead | Quarterly

## FMEA
FAILURE MODES & EFFECTS ANALYSIS (Step 13) — Severity × Occurrence × Detection = RPN
Scale 1–10. RPN >= 200 = critical action. 100–199 = priority. <100 = monitor.
ID | Process step | Failure mode | Effect | Sev (1–10) | Cause | Occ (1–10) | Current control | Det (1–10) | Recommended action | RPN | Priority
1 | Phase E — ERP integration | Q1 (integration approach) not resolved before DX build starts | 10–12 wk app build blocked or rebuilt | 9 | IT/DX coordination gap; no decision forcing function | 6 | Tracker tasks E.1/E.4 listed; PRD note 'do not start DX build' | 4 | Force decision meeting; document API option with IT before any other phase | 216 | CRITICAL
2 | SC single point of failure | Calo unavailable (sick/leave) with no app permissions delegated | Workshop halts; field workers blocked; assets sit idle | 8 | Single Stock Controller; Workshop Handler has no app permissions | 5 | Escalation to supervisor mentioned in SOP 1 | 6 | Provision backup-SC AppSheet role; cross-train 1 backup; document weekend cover | 240 | CRITICAL
3 | Item naming / catalog ambiguity | Worker requests 'wrong' part using informal name | Wrong parts issued; rework; trust erosion | 6 | Suppliers use multiple names; informal naming in books | 7 | Phase A renaming to OEM names underway | 3 | Photos + synonyms field in Parts_Catalog; pre-defined defect→category map | 126 | PRIORITY
4 | ERP sync failure (silent) | EResource_Updated stays = No, undetected for hours | Inventory drift; procurement decisions wrong; rework | 8 | Async automation bot; no retry/alert defined | 4 | SOP 3 says halt issuances on sync fail | 7 | Add 5-min watchdog; auto-retry 3x; SMS escalation on persistent fail | 224 | CRITICAL
5 | Phase C catalog data quality | Wrong item codes / SKUs imported to app | Issuances post to wrong ERP line; reconciliation nightmare | 8 | Manual cataloguing of 100–500 items by one person | 5 | Spreadsheet review | 5 | Two-person verify of every item code before import; UAT cross-check | 200 | CRITICAL
6 | Inventory book inflation | E-resource shows phantom stock cleared from legacy assets | Procurement skips needed orders; stockout | 7 | Historical accumulation of un-issued items | 7 | Phase A clearout already underway | 4 | Account-validated clearout (in progress); rebaseline at Phase F | 196 | PRIORITY
7 | Phase B inspector inconsistency | Two inspectors classify defects differently | Parts demand list is biased; thresholds wrong | 5 | Two inspectors (Calo + Thakur), no calibration | 6 | Phase B SOP exists | 5 | Run 1 calibration day; both inspect same 5 assets; reconcile | 150 | PRIORITY
8 | Field worker non-adoption | Workers bypass app (call SC directly) | Defeats the entire system; metrics invalid | 9 | Old habits; informal culture | 6 | Pre-launch briefings planned | 6 | SOP 1 enforcement; SC must refuse undocumented requests; visible scoreboard | 324 | CRITICAL
9 | Connectivity outage in yard | Request not synced; field worker doesn't know | Delayed fulfilment; double-submission | 5 | Yard signal known to be patchy | 6 | PRD NFR: 'offline queue' | 5 | Verify offline behavior in UAT; add sync-status indicator | 150 | PRIORITY
10 | AppSheet platform limits hit | 50+ requests/day breach AppSheet quota | Slowness, dropped writes | 6 | AppSheet free/team-plan limits | 3 | PRD NFR; DX Team aware | 5 | Stress test at 100/day in UAT; budget for plan upgrade | 90 | MONITOR
11 | Returns abuse / fraud loophole | Workers 'return' parts that were never returned to inflate inventory | Theft cover; inventory inflation | 8 | Mandatory reason exists but is text-only | 3 | Mandatory reason field | 6 | Photo evidence on return >$X; weekly spot audit of returns | 144 | PRIORITY
12 | Buggy/SS Workshop section mix-up | Issuance posts to wrong ERP section | Both sections wrong; book-vs-reality drift | 7 | Two parallel sections; manual mapping | 4 | Phase E.2 explicit confirm | 5 | Test issuance per section in UAT; lock category→section mapping | 140 | PRIORITY
13 | Photography backlog | Phase D slips; app lacks photos at go-live | Workers can't ID parts visually; reverts to voice/walk-up | 4 | Photography concurrent with C; 3–5 photos/day cadence is slow | 6 | Tracker tasks 21–27 | 4 | Batch photo session w/ phone stand; 1 day = 100 items | 96 | MONITOR
14 | Defect→category mapping wrong | Pre-filtered catalog hides relevant parts from worker | Worker thinks part missing → calls SC anyway | 5 | Initial mapping is 'starting point' | 6 | PRD §11 | 5 | Weekly map review for first 6 weeks; add 'Show all' override | 150 | PRIORITY
15 | 30+ min ERP batch persists post-launch | Manual interim runs in parallel beyond plan | SC overhead doubles; staff resent system | 6 | Migration risk | 4 | Plan says manual closed at week 14 | 3 | Hard-stop ceremony; remove SC's ERP access on go-live+14d | 72 | MONITOR
16 | Photo storage / Drive permissions break | Photos un-viewable in app on go-live day | Visual catalog dead; UX broken | 6 | Drive folder permission gotchas | 3 | Tracker task 25/27 | 4 | Pre-go-live permission audit; test on 3 worker devices | 72 | MONITOR

## ThroughputEcon
THROUGHPUT ACCOUNTING — T / OE / I model (Step 12)
Goldratt framing: T = Throughput (revenue-enabling output), OE = Operating Expense, I = Inventory. Decisions evaluated on impact to T per constraint-hour.
INPUTS |  |  | Notes
Fleet assets enabling rental revenue | 500 |  | PRD §1
Avg rental yield per asset per month (AED) | 3000 |  | Placeholder — Calo to confirm. Italic = assumption.
Estimated revenue-loss per asset-day grounded | 100 |  | approx = monthly yield / 30 days
Avg asset-days lost per stockout event | 1.5 |  | Estimate — until part arrives
Estimated stockout events/month pre-launch | 8 |  | Estimate — no monitoring today
Estimated stockout events/month post-launch | 1 |  | Target — reorder alerts effective
SC daily ERP batch time (min) — pre-launch | 35 |  | Mid-point of 30–45 min
SC fully loaded cost (AED/hour) | 80 |  | Placeholder — Calo to confirm
Field worker fully loaded cost (AED/hour) | 50 |  | Placeholder
Avg field worker walk-back trips/day pre-launch | 6 |  | Anecdotal — workers walking to workshop and back
Walk-back duration each (min) | 15 |  | Estimate (avg yard distance)
Manual log catch-up admin (min/day) post-launch | 0 |  | Eliminated
COMPUTED — MONTHLY (AED unless stated) | Pre-launch | Post-launch | Delta / month (savings)
Revenue lost to stockouts (AED/month) | 1200 | 150 | 1050
SC ERP-batch hours/month | 12.8333 | 0 | 12.8333
SC time value (AED/month) | 1026.6667 | 0 | 1026.6667
Worker walk-back hours/month | 33 | 9.9 | 23.1
Worker walk-back value (AED/month) | 1650 | 495 | 1155
TOTAL MONTHLY NET SAVINGS (AED) |  |  | 3231.6667
ANNUAL NET T-IMPACT (AED) |  |  | 38780
OPERATING EXPENSE — One-time (AED) | Amount | Notes
AppSheet app build (DX Team internal) | 0 | Internal team; opportunity cost only
AppSheet licensing — 1 year | 5000 | Estimate; confirm with DX
Stickers / labels / shelving | 1500 | Phase setup
Photo setup (lightbox + smartphone stand) | 500 | One-time
Training time (workers x 15 min) | 0 | Internal
TOTAL ONE-TIME OE | 7000
Payback (months) | 2.1661 | OPEX / monthly net savings; 0 if no savings yet

## Capacity
CAPACITY MODEL — Little's Law & M/M/1 queueing for the Stock Controller (Step 9)
Verifies the SC is the constraint and tells you at what request volume the system breaks.
INPUT — arrival side | Value | Notes
Average requests per day (lambda) | 30 | Mid-range of expected; PRD NFR caps at 50+
Working hours per day | 9 | 07:00–16:00 typical workshop shift
Arrival rate λ (requests/hour) | 3.3333
INPUT — service side
SC mean service time per request (min) | 12 | Decide, locate, hand-over, log
Service rate μ (requests/hour) | 5
RESULTS
Utilization ρ = λ/μ | 0.66667 | Must be < 0.85 to avoid runaway queues
Avg # in system L = ρ/(1-ρ) | 2 | M/M/1 formula
Avg time in system W (min) = L/λ × 60 | 36 | Total request cycle time including wait
Avg wait in queue Wq (min) | 24
Probability of stable queue (ρ<1)? | STABLE
Max sustainable arrival rate (req/day, ρ=0.85) | 38.25
WHAT-IF: when do we need a backup SC?
Trigger: ρ exceeds (0.85) | NO
Trigger: requests/day exceeds | 38.25

## Decision
RECOMMENDATION RANKING — Leverage × Feasibility × Time-to-value (Step 21)
Each scored 1–5. Score = L × F × (6-TTV) so faster = better. Sorted high→low.
ID | Recommendation | Leverage (1-5) | Feasibility (1-5) | Time-to-value (1=fast 5=slow) | Owner | Success metric | Risk | Score | Rank
R1 | Resolve Q1 (ERP integration approach) BEFORE DX build starts | 5 | 4 | 1 | Calo + Vincent + IT + DX | Decision documented & signed | DX build rework | 100 | 1
R2 | Provision backup-SC role + cross-train 1 person | 4 | 4 | 2 | Calo + Ops Lead | Backup-SC handles 1 shift/wk in parallel run | Resistance from cross-trainee | 64 | 10
R3 | Embed time-and-motion telemetry in AppSheet (free; see TimeMotionDesign sheet) | 5 | 5 | 2 | DX Team + Calo | 10 measurement points live by Week 9 build | Scope creep with DX | 100 | 1
R4 | Two-person verify on every catalog item code before import | 4 | 5 | 1 | Calo + Mohamed Thakur | 0 wrong item codes in UAT | Slower Phase C; mitigated by structured cross-check | 100 | 1
R5 | Inspector calibration day for Phase B (Calo + Thakur on same 5 assets) | 4 | 5 | 1 | Calo + Thakur | ≤10% classification variance | 1-day delay to Phase B | 100 | 1
R6 | Watchdog + SMS escalation on ERP sync failure (>5 min unsynced) | 5 | 4 | 3 | DX Team | Test failure triggers SMS in UAT | Bot complexity | 60 | 12
R7 | 'Show all' override + synonym field on Parts_Catalog | 4 | 5 | 2 | DX Team + Calo | Workers find part in <60 sec in UAT | Catalog hygiene effort | 80 | 7
R8 | Batch photography session (1 day = 100 items) | 3 | 5 | 1 | Calo | 100 items photographed in 1 day | Quality vs speed | 75 | 9
R9 | Stockout 'lost-hours' capture on every reject/partial | 4 | 4 | 2 | DX Team | Field reads on Reject events | Worker friction | 64 | 10
R10 | GPS-stamp travel time + repeat-trip detection (within-app) | 4 | 4 | 3 | DX Team | Travel time + repeat-trip KPIs live | Privacy concerns to manage | 48 | 14
R11 | Visible workshop scoreboard (TV showing daily KPIs) | 3 | 4 | 4 | Calo + Ops Lead | Scoreboard up + viewed daily | Sustaining engagement | 24 | 16
R12 | Pre-launch 'photo evidence' rule for returns > AED X threshold | 3 | 5 | 2 | Calo | Returns photo logged in app | Worker minor friction | 60 | 12
R13 | Returns weekly spot audit (5% sample) | 4 | 5 | 1 | Calo + Ops Lead | Audit report each Fri | Calo workload | 100 | 1
R14 | Lock category → ERP section mapping (Buggy / SS Workshop) | 5 | 5 | 2 | Calo + IT | Mapping signed off + tested | Late binding pain | 100 | 1
R15 | Force-stop ceremony at week 14 to kill manual ERP batch | 4 | 5 | 4 | Calo + Vincent | SC's ERP write access removed Week 14 | Backsliding | 40 | 15
R16 | Add 'Defect-to-Request latency' as Phase 2 KPI (signal of catalog UX issues) | 4 | 5 | 2 | DX Team | Field auto-captured; appears in scorecard | Statistical noise at low volume | 80 | 7

## WastePareto
TIMWOODS WASTE AUDIT (Step 8) — current state, ranked
Pre-launch and during the interim. Severity 1–10, frequency observations per day.
TIMWOODS category | Observation | Severity (1-10) | Frequency (events/day) | Notes | Score (S×F) | Cumulative %
T — Transport | Workers walking from yard to workshop multiple times per defect (no app, no anticipation) | 7 | 8 | Tracked walk-back trips; ~6/day across crew | 56 | 15.56%
I — Inventory | Phantom/legacy stock in e-resource books; obsolete items not yet cleared | 8 | 10 | Phase A clearout (15/36 done as of 5/26) | 80 | 22.22%
M — Motion | SC manually walking to physical bin for each issuance with no pre-staged batching | 5 | 8 | Mitigated post-launch by Location_Code | 40 | 11.11%
W — Waiting | Workers waiting at workshop door for SC to return; no in-app status | 7 | 9 | Anecdotal; SOP 1 'door locked when SC absent' | 63 | 17.5%
O — Overproduction | Workers requesting 'extra to be safe' parts they never use → returns | 4 | 4 | Mandatory return reason captures but doesn't prevent | 16 | 4.444%
O — Overprocessing | Daily manual ERP batch update (30–45 min) for what the app will do automatically | 8 | 5 | Quoted from Process Doc — 'main pain point' | 40 | 11.11%
D — Defects | Wrong parts issued from informal/ambiguous names → rework | 7 | 5 | PRD §11 defect→category map mitigates | 35 | 9.722%
S — Skills (under-utilized) | SC capacity wasted on manual ERP entry that the bot will eliminate | 6 | 5 | approx 8 hrs/wk SC time freed | 30 | 8.333%

## TimeMotionDesign
TIME-AND-MOTION STUDIES — BUILT INTO THE APPSHEET APP (no clipboard required)
This is the architecture for embedding Gilbreth/MTM-style time-and-motion measurement INSIDE the operational app — zero extra clicks for workers/SC, full data capture by design.
Principle 1 | Every transaction already has timestamps. Differences between timestamps = free metrics. No worker action required.
Principle 2 | GPS lat/lng on every Request submit + every Status change converts the app into a passive motion sensor.
Principle 3 | Location codes + timestamps = Spaghetti Diagram of the SC's day, auto-generated.
Principle 4 | Pre-launch (Phase F): manually time 30 representative issuances. Post-launch: same data captured automatically. Direct A/B for ROI defence to Vincent + John.
Principle 5 | Make it visible. A simple dashboard tile per metric. What gets measured & seen gets improved.
MEASUREMENT POINTS — 14 free metrics, captured automatically
ID | Metric | How captured | Why it matters | Where in flow | Implementation cost
TM-01 | Notification latency | T_submit (REQ row created) → T_notif (push delivered) | Diagnoses DX/AppSheet delivery health; PRD target <2 min | Phase 2-3 | Auto (built-in)
TM-02 | Defect-to-Request latency | T_defect_marked → T_request_submitted | Workers procrastinating? Catalog hard to navigate? | Phase 1-2 | Auto (built-in)
TM-03 | Decision latency | T_notif → T_SC_decision (Accept/Partial/Reject) | SC overloaded? Catalog data missing? | Phase 3 | Auto (built-in)
TM-04 | Handover latency | T_decision → T_handover_complete (worker signs) | Physical pick + hand-over efficiency | Phase 3-4 | Auto (built-in)
TM-05 | Closeout latency | T_handover → T_status=Completed | Admin tail; usually trivial post-bot | Phase 4-5 | Auto (built-in)
TM-06 | Total request cycle time | T_submit → T_status=Completed | The headline KPI | All | Auto (built-in)
TM-07 | Travel time (GPS) | GPS at submit (asset) vs GPS at handover (workshop) | Layout efficiency; identifies long-distance assets | Phase 1-4 | Auto (GPS field)
TM-08 | Repeat-trip detection | Same worker + same plant + new request <24h after Completed | Poor defect diagnosis or partial issuance signal | Phase 1-2 | AppSheet bot (post-write)
TM-09 | Lost productive hours (stockout) | On Reject/Partial w/ reason=OOS, capture estimate from worker (1 dropdown) | Throughput accounting — converts to AED | Phase 3 reject branch | 1 extra dropdown — 2 sec
TM-10 | SC standard work timing | Optional: SC taps 'Start Pick' / 'End Pick' in SC view | Builds Calo's personal time-standard library; MTM-style | Phase 3-4 (SC side) | 2 extra taps — opt-in
TM-11 | Catalog navigation telemetry | # of category taps, search resets, time-on-screen before Add | UI friction → which parts need better naming/photos | Phase 2 | AppSheet event log
TM-12 | Location-code pick path | Each issuance line item logs Location_Code; daily heatmap | Golden-zone optimization (Gilbreth motion study output) | Phase 4 | Auto (already in data model)
TM-13 | Workshop pick-path spaghetti | Sequence of Location_Codes touched in SC's shift | Spaghetti diagram auto-generated as SVG | Phase 3-4 | Daily bot run, SVG to Drive
TM-14 | Pre-vs-post baseline study | 30 manually timed issuances pre-launch (Phase F) — same auto-captured post-launch | ROI defence; signed evidence for Vincent + John | Phase F + Week 14 | 1 day Calo manual
DATA MODEL ADDITIONS — minimal schema deltas to support all 14 metrics
Table | New / used fields | Implementation
Parts_Requests | T_submit (auto), T_notif (auto), GPS_submit_lat, GPS_submit_lng | AppSheet built-ins + GPS field type
Issuance_Tickets | T_decision (auto), T_handover (Save action), T_complete (auto), GPS_handover | AppSheet built-ins + action timestamp
Request_Line_Items | Location_Code_at_Pick (lookup), Pick_Start, Pick_End (SC opt-in actions) | Existing field + 2 optional tap actions
Returns | Return_Reason (existing), Photo_Evidence (new, conditional on AED threshold) | Image field
Catalog_NavLog (new tiny table) | Worker_ID, Session_ID, Tap_Sequence (CSV), T_session_start, T_added_to_cart | AppSheet event sink — 1 row per session
DERIVED METRICS — calculated views (no extra capture)
Derived metric | Calculation | Why
Cycle time histogram | Bin(T_complete - T_submit, 5-min buckets) | Identify long-tail outliers for RCA
P50 / P95 latency per stage | PERCENTILE on TM-01...TM-05 | SLA reporting
Worker-pareto by repeat-trips | GROUP BY Worker_ID, COUNT(TM-08) | Coaching targets
Parts-pareto by stockout-AED | GROUP BY Part_ID, SUM(TM-09 dollars) | Procurement priorities
Location heatmap (Gilbreth) | GROUP BY Location_Code, COUNT, daily | Move top-20 to golden zone
Spaghetti SVG | ORDER BY T_pick, sequence Location_Codes → polyline | Visual motion-waste detection
Capacity warning | ρ (utilization) crosses 0.85 (see Capacity sheet) | Trigger backup-SC scheduling
Defect→Request UX score | Inverted P50(TM-02). Slow = bad UX | Drives catalog/category map iteration

## ControlPlan
CONTROL PLAN — measurement system (Step 20)
Control item | Owner | Method | Cadence | Pass criterion | Reaction plan if fail
Daily request queue review | Calo | App dashboard | On open of day | 0 unresolved >2h | Escalate to supervisor if >2h
Daily ERP sync check | Calo + DX | EResource_Updated flag | End of shift | 100% | Halt issuances, page IT
Weekly KPI scorecard review | Calo + Ops Lead | KPI sheet of this workbook | Friday 30 min | All Green or action plan | Escalate Reds
Weekly RCA of P95 outlier requests | Calo | Cycle time histogram | Friday 30 min | 1 root cause documented + action | Add to improvement backlog
Monthly full stock count | Calo (+ helper) | SOP 6 procedure | Last Friday of month | >=95% accuracy | Investigate >5% variance
Monthly KPI vs target review | Ops Lead | KPI sheet trend | 1st Tuesday | >=80% KPIs green | Re-plan Reds
Monthly low-stock alert hit-rate audit | Calo | App alert log vs stockout events | 1st Wednesday | 100% alerts pre-stockout | Adjust thresholds
Quarterly catalog hygiene review | Calo | Synonym list, photo coverage, defect→category map | Quarterly | 100% items with photo | Backlog any gaps
Quarterly SOP review | Ops Lead | SOPs doc | Quarterly | All SOPs reviewed; changes versioned | Update + re-circulate
Annual control plan review | Ops Lead | This sheet | Annual | Plan updated | —
Annual capacity model refresh | Ops Lead | Capacity sheet inputs | Annual | ρ < 0.85 sustained | Add backup-SC capacity

## ImplementationPlan
IMPLEMENTATION — Kotter 8 + ADKAR mapped to milestone tracker (Step 19)
Kotter step | ADKAR phase | Action | Maps to Tracker / Doc | Owner | Timing
Kotter 1 — Urgency | ADKAR — Awareness | Site brief + 'one slide of pain' (30-45 min daily ERP, lost rentals from stockouts) | Already implicit in project | Calo + Vincent | Week 0 (done)
Kotter 2 — Coalition | ADKAR — Awareness | Named coalition: Calo, Vincent (sponsor), John (ops), Mohamed Thakur (peer), DX Team, IT | Documented in PRD/Tracker | Calo | Week 0 (done)
Kotter 3 — Vision | ADKAR — Desire | One-page vision: 'every part issued is logged, every asset's needs are visible, SC works remote with confidence' | PRD §1 covers it | Calo | Week 0 (done)
Kotter 4 — Communicate vision | ADKAR — Desire | Pre-launch briefings (PRD §17 — 15 min each); workshop poster | Tracker task 72 | Calo | Week 11–12
Kotter 5 — Empower action | ADKAR — Knowledge + Ability | Worker briefings + SC walkthrough (Tracker 72-73); SOP cards at workshop counter; pilot during parallel run | Tracker 72-73-74 | Calo + DX Team | Week 12
Kotter 6 — Short-term wins | ADKAR — Ability + Reinforcement | Daily KPI scoreboard during parallel run; weekly 'wins' Slack/WhatsApp message | — | Calo | Week 12-14
Kotter 7 — Consolidate gains | ADKAR — Reinforcement | 30-day review (Tracker task 77) + iterate on defect→category map + add backlog requests to roadmap | Tracker 77 | Calo | Week 16
Kotter 8 — Anchor in culture | ADKAR — Reinforcement | SOPs locked in; SOPs re-reviewed every 6 months; KPI scoreboard always visible; new joiners trained on app first | Continuous | Ops Lead | Ongoing
RISK MGMT | — | Run risk register weekly during launch; review FMEA monthly post-launch | FMEA sheet | Calo + Ops Lead | Ongoing
CHANGE LOG | — | Version control on PRD/SOPs/Process via Google Drive; never overwrite — append v1.2 → v1.3 | Docs | Calo | Ongoing