AL LAITH SITE SERVICES

Workshop Stock Control

COEEx OS — Full-System Operational Diagnosis (21-step)

Owner: Calo (Site Services Ops) · Sponsor: Vincent Nibbering · Sign-off: John Maddern

Generated: 26 May 2026 · Inputs: PRD v1.1, SOPs v1.0, Process Doc v1.2, Milestone Tracker 5/13/26

This report runs the full 21-step COEEx OS diagnostic on the Workshop Stock Control project. It treats the existing PRD/SOPs/Process docs as ground truth, then layers an operational-excellence lens: waste, bottlenecks, root causes, throughput economics, FMEA, and an embedded time-and-motion measurement architecture that lives inside the AppSheet build (no clipboard, no overhead).

Companion files:

Workshop_Stock_FullSystem_Diagnostic.xlsx — KPI scorecard, FMEA, throughput economics, capacity model, decision matrix, waste Pareto, time-motion design, control plan, implementation plan

Workshop_Stock_Process_Maps.html — current-state VSM, fishbone, future-state VSM, time-motion overlay, sample spaghetti diagram

Workshop_Stock_Exec_OnePager.docx — A3 summary for Vincent / John

Steps 1–6 · Scope, Objective, Data, Constraints, Skills, Tools

Step 1 — Observation (mental Gemba walk)

Workshop sits adjacent to a 500+ asset yard (cabins, ablution units, golf buggies, utility vehicles, flatpacks). Pre-launch the workshop store has no access controls, no transactional record, and no automated link to the e-Resource ERP. Field workers ad-hoc walk to the workshop, ask the Stock Controller (Calo, single person) verbally, take parts, return to their job. e-Resource is updated end-of-day by Calo in a 30–45 minute manual batch when issuances exceed twenty. Two inspectors (Calo, Thakur) are PDI-ing every asset in parallel — generating the parts-demand list that will populate the catalog and the reorder thresholds. The AppSheet app build (10–12 weeks, DX Team) has not started because the ERP integration approach (Q1) is unresolved. Pre-launch programme is live: Phase A (asset clearout) and Phase B (yard PDI) are in progress; Phases C–F and labeling are early/pending; Calo is the only person on the critical path for most pre-launch tasks.

Step 2 — Objective (SMART)

By 1 September 2026 (Week 14 from project start), Al Laith Site Services will operate a closed-loop digital workshop stock system in which (a) 100% of issued parts are logged in real time with worker, asset, job and timestamp; (b) e-Resource inventory updates within 60 seconds of each issuance with ≥ 99.5% sync success; (c) median request cycle time ≤ 30 min and P95 ≤ 60 min; (d) inventory accuracy ≥ 95% at first monthly count; (e) low-stock alerts trigger before 100% of stockouts; (f) field-worker training to competency ≤ 15 minutes — supported by an embedded time-and-motion measurement layer that quantifies pre-vs-post productivity for management sign-off.

Step 3 — Baseline data

See Baseline tab of the diagnostic workbook for full table. Highlights:

| Metric | Pre-launch | Target post-launch | Source |
| --- | --- | --- | --- |
| Parts issued with no digital record | 100% | 0% | PRD §17 |
| Time: request → SC notified | N/A (verbal) | < 2 min | PRD §17 |
| Manual ERP batch time/day @20+ | 30–45 min | 0 | Process Doc |
| ERP auto-update | 0% | 100% | PRD §17 |
| Low-stock alerts before stockout | 0% (no monitoring) | 100% | PRD §17 |
| Stock Controller headcount | 1 | 1 (+1 cross-trained backup) | SOPs |
| Catalog SKUs | Unknown | 100–500 with photos | Process §C |
| Pre-launch programme duration | — | 8–12 wks | Tracker |
| App build duration | — | 10–12 wks | PRD §12 |

Step 4 — Constraints

Mapped on the future-state diagram (Process Maps file, §3). Three binding constraints stand out:

C1 — Stock Controller capacity. A single Calo is on the critical path for inspection, cataloguing, photography, labelling, app UAT, ERP coordination AND day-to-day SC duties. M/M/1 model on the Capacity sheet shows the workshop becomes unstable above ~32 requests/day at 12-minute service time.

C2 — ERP integration decision (Q1). The PRD itself instructs 'Do not start the DX build until Q1 is resolved.' Every downstream day until this is settled compounds against the 10–12 wk build window.

C3 — Catalog data quality. Wrong item codes at import would silently corrupt every subsequent ERP write. Cataloguing is single-person manual today.

Step 5 — Skill manifest (COEEx OS skills invoked)

diagnostics/operational-diagnosis-protocol · tools/tool-selection-protocol

gemba-walk · smart-goals · demand-analysis · kpi-dashboard

theory-of-constraints · bottleneck-analysis · queueing-theory-littles-law

value-stream-mapping · process-mapping · timwoods-waste-identification

root-cause-5-whys · fishbone-ishikawa · human-factors-analysis · respect-for-people-principle

economic-throughput-accounting · decision-theory · risk-assessment · fmea

sop-generator-tool-aware · figma-component-library (rendered as SVG) · gsheets-tool-intel (rendered as XLSX)

kpi-builder-tool-aware · automation-opportunity-analysis · kotter-8-steps · adkar · project-charter

control-plan · operational-scorecard · executive-report-tool-aware · a3-problem-solving

Step 6 — Tool assignment per deliverable

| Deliverable | Tool | File |
| --- | --- | --- |
| KPI scorecard, FMEA, capacity, decision, waste pareto, time-motion design, control plan, implementation plan | Excel (xlsx) | Workshop_Stock_FullSystem_Diagnostic.xlsx |
| Current-state VSM, fishbone, future-state VSM, time-motion overlay, spaghetti diagram | HTML/SVG | Workshop_Stock_Process_Maps.html |
| Full diagnostic narrative + recommendations | Word (docx) | this file |
| A3 executive one-pager | Word (docx) | Workshop_Stock_Exec_OnePager.docx |

Note: production-grade tools (Google Docs, Sheets, Figma, Power BI) are listed in the protocol; this engagement delivers in offline-portable Office formats per the user's environment. All artefacts can be uploaded to Google Drive without re-formatting.

Steps 7–10 · Process Map, Waste, Bottlenecks, Root Cause

Step 7 — Process map (current state)

See Workshop_Stock_Process_Maps.html §1 for the full SVG. In summary: today the value stream is a sequence of unmeasured verbal handoffs across three swimlanes (Field Worker / Stock Controller / ERP). The ERP swimlane is fed not by transactional events but by a single end-of-day manual batch — the dominant red node on the map.

Step 8 — Waste audit (TIMWOODS) + Pareto

Full table in WastePareto sheet. Top three waste sources by Severity × Frequency:

| Rank | TIMWOODS | Observation | Score |
| --- | --- | --- | --- |
| 1 | Inventory | Phantom/legacy stock in e-resource books; obsolete items not yet cleared | 80 |
| 2 | Waiting | Workers waiting at workshop door for SC with no in-app status visibility | 63 |
| 3 | Transport | Workers walking yard ↔ workshop multiple trips per defect | 56 |
| 4 | Overprocessing | Daily 30–45 min manual ERP batch update | 40 |
| 5 | Motion | SC walking shelf-by-shelf with no pre-staged pick batching | 40 |
| 6 | Defects | Wrong parts from informal names → rework | 35 |
| 7 | Skills (under-used) | SC spends ~8 hrs/week on ERP entry the bot will eliminate | 30 |
| 8 | Overproduction | Workers requesting 'extra to be safe' → returns | 16 |

Step 9 — Bottleneck location & classification

Two bottlenecks, in priority order:

Primary bottleneck (constraint of constraints): the Stock Controller — Calo. Capacity sheet M/M/1 model shows λ=30 req/day, μ=5 req/hour at 12 min service ⇒ ρ ≈ 0.67, W ≈ 36 min, Wq ≈ 24 min. At 50 req/day (PRD NFR ceiling) ρ jumps to 1.11 — UNSTABLE; queue diverges. Action: stop being clever — bring a cross-trained backup-SC online before crossing 32 req/day, and design the app so the SC can work remote (already in PRD).

Secondary bottleneck (pre-launch only): the ERP integration decision (Q1). It blocks DX Team mobilisation. Classified as a policy/decision bottleneck, not a capacity one — 1 meeting can break it. Cost of delay = entire 10–12 wk app build pushes right.

Step 10 — Root cause analysis (5-Whys + Fishbone)

Fishbone in Process Maps §2 covers six bones (People, Process, Materials/Data, Technology, Measurement, Environment). Verified root causes via 5-Whys:

RC-1 · No closed-loop transaction system.

Why parts go missing? No transaction record.

Why no record? No system requires it.

Why no system? Historic culture + no field-friendly UX into the existing ERP.

Why no field-friendly UX? Workers were never expected to use e-Resource — it's an accounting system.

Why never expected? No-one architected a worker-facing layer. ✓ Root cause.

RC-2 · Worker ↔ ERP usability gap.

Why workers don't log? UI complex, in English, desktop-oriented.

Why? ERP is generic, not mobile-/bilingual-/photo-driven.

Why never adapted? No requirement was raised; no one owned the worker layer.

Why no owner? Site Services had no ops-tech role. ✓ Root cause.

RC-3 · Single Stock Controller bottleneck.

Why SC overloaded? One person owns every issuance.

Why one? Historical staffing + small team.

Why no backup? No backup role defined; weekend cover undecided in PRD.

Why undecided? Project scope deferred it as a 'go-live' item. ✓ Root cause — bring it forward.

Steps 11–13 · Human Factors, Economics, Risk

Step 11 — Human-factor assessment

The system rests on real people. Assessment by role:

| Role | Strengths today | Friction / risk | Mitigation |
| --- | --- | --- | --- |
| Field worker | Job-context expertise; knows the asset | Limited literacy with ERP; informal naming culture; signal patches in yard | Photo-first catalog; pre-filtered defect→category map; offline queue; bilingual UI |
| Stock Controller (Calo) | High ownership; institutional knowledge of every SKU | Single point of failure; risks burnout from 30–45 min nightly ERP batch + full SC duties + pre-launch programme | Cross-train backup-SC now; offload ERP batch to bot at launch; protect time during pre-launch by parking non-critical Phase C/D tasks |
| Workshop Handler (remote scenario) | Physical presence when SC remote | Zero app permissions today; SC must trust verbally | Define narrow app role for handover-confirm only; keep authority with SC |
| Inspectors (Calo + Thakur) | Two-person coverage of yard PDI | Calibration risk — different defect calls bias the demand list | 1-day calibration: same 5 assets, reconcile classifications before Phase B completes |
| DX Team (Soluchan) | AppSheet build capability; access to BinaryData/Drive | External dependency; not embedded in workshop reality | Calo on-site review every 2 wks; UAT scripts written by Calo not DX |
| IT / e-Resource admin | Owns ERP | Unclear ownership of integration approach (Q1) | Force Q1 decision meeting; document API option with named owner |

Respect-for-people principle: every recommendation in this report names an owner — work is added to people who already have plates that are full; either we replace something on their plate, or we add headcount, or we defer.

Step 12 — Throughput economics (T / OE / I)

Full model in ThroughputEcon sheet (values flagged italic are placeholder assumptions — Calo to update). Decision frame:

T (Throughput) gain comes from: (a) stockouts prevented → rental revenue protected; (b) SC time recovered from manual ERP batch; (c) worker walk-back trips reduced (assumed 70% reduction post-launch).

OE (Operating Expense): app build is internal; named one-time costs are AppSheet licensing (~AED 5k/yr est), labels/stickers (~AED 1.5k), photo setup (AED 500), training (internal time). Total one-time ≈ AED 7k.

I (Inventory): post-launch inventory will DROP because phantom stock is cleared and reorder thresholds prevent over-stocking; freed working capital is an additional benefit not modelled here.

Decision rule: payback months = One-time OE ÷ monthly net T-savings. With placeholder assumptions the workbook shows payback ≪ 1 month — i.e. the app pays for itself in stockout-prevention alone, with SC and worker productivity as gravy. Calo: please replace the BLUE placeholders with confirmed wage rates and yield estimates and re-share before sign-off.

Step 13 — Risk register (FMEA)

16 failure modes scored on Severity × Occurrence × Detection. Top five by RPN (full table in FMEA sheet):

| Rank | Failure mode | RPN | Recommended action |
| --- | --- | --- | --- |
| 1 | Field-worker non-adoption (call SC directly, bypass app) | 324 | SC must refuse undocumented requests; visible scoreboard; SOP 1 enforcement |
| 2 | SC single point of failure (Calo unavailable) | 240 | Provision backup-SC role; cross-train 1 person; document weekend cover |
| 3 | ERP sync failure silent for hours | 224 | 5-min watchdog; auto-retry 3x; SMS escalation on persistent fail |
| 4 | Q1 (ERP integration) not resolved before DX build starts | 216 | Force decision meeting; document API option with IT before any other phase |
| 5 | Catalog data quality — wrong item codes imported | 200 | Two-person verify of every item code before import; UAT cross-check |

Steps 14–17 · Documentation, Visuals, Spreadsheets, Dashboards (generated)

This section catalogues what was produced. The artefacts themselves are the deliverables:

| Step | Deliverable | Location |
| --- | --- | --- |
| 14 | Diagnostic report (this document) | Workshop_Stock_FullSystem_Diagnostic_Report.docx |
| 14 | A3 executive one-pager | Workshop_Stock_Exec_OnePager.docx |
| 15 | Current-state VSM (SVG) | Process_Maps.html §1 |
| 15 | Fishbone (SVG) | Process_Maps.html §2 |
| 15 | Future-state VSM (SVG) | Process_Maps.html §3 |
| 15 | Spaghetti diagram mock-up | Process_Maps.html §5 |
| 16 | KPI tracker (16 KPIs, RAG) | Diagnostic.xlsx — KPI sheet |
| 16 | FMEA risk register (16 entries) | Diagnostic.xlsx — FMEA sheet |
| 16 | Throughput economics model | Diagnostic.xlsx — ThroughputEcon sheet |
| 16 | Capacity model (Little's Law + M/M/1) | Diagnostic.xlsx — Capacity sheet |
| 16 | Decision matrix (16 recs, scored) | Diagnostic.xlsx — Decision sheet |
| 16 | TIMWOODS waste Pareto | Diagnostic.xlsx — WastePareto sheet |
| 16 | Time-motion design (14 metrics) | Diagnostic.xlsx — TimeMotionDesign sheet |
| 17 | Operational scorecard (live) | Diagnostic.xlsx — KPI sheet (Update Current each cycle) |

Power BI is not generated here because no live data exists yet; the KPI sheet is the interim scorecard until app telemetry is live, at which point the same column structure imports straight into Looker Studio / Power BI without rework.

Steps 18–20 · Automation, Implementation, Measurement

Step 18 — Automation roadmap (including Time-and-Motion studies)

This is the section the PRD did not yet cover. Premise: every measurement we add must be a free side-effect of the app already doing its job — zero extra clicks for workers. Five principles + 14 measurement points. Full sheet: TimeMotionDesign.

Principles:

P1 — Every transaction already has timestamps; differences = free metrics.

P2 — GPS lat/lng on submit + status change = the app becomes a passive motion sensor.

P3 — Location codes + timestamps = auto-generated Spaghetti Diagram of the SC's day.

P4 — Phase F manual timing of 30 issuances becomes the baseline for a direct pre-vs-post A/B that defends ROI to Vincent and John.

P5 — Make it visible. One dashboard tile per metric.

The 14 measurement points (TM-01 … TM-14):

| ID | Metric | Capture mechanism | Cost to add |
| --- | --- | --- | --- |
| TM-01 | Notification latency | T_submit → T_notif (built-in timestamps) | Free |
| TM-02 | Defect-to-Request latency | T_defect_marked → T_request_submitted | Free |
| TM-03 | Decision latency | T_notif → T_SC_decision | Free |
| TM-04 | Handover latency | T_decision → T_handover | Free |
| TM-05 | Closeout latency | T_handover → T_complete | Free |
| TM-06 | Total cycle time | T_submit → T_complete (the headline KPI) | Free |
| TM-07 | Travel time + distance (GPS) | GPS on submit vs handover | 1 GPS field |
| TM-08 | Repeat-trip detection | Same worker + plant within 24h | 1 AppSheet bot |
| TM-09 | Stockout AED-impact | On Reject reason=OOS, capture est. lost-hours from worker | 1 dropdown (2 sec) |
| TM-10 | SC pick-time standard | Optional 'Start Pick' / 'End Pick' taps | 2 taps, opt-in |
| TM-11 | Catalog navigation UX | Tap-sequence + time-on-screen log | 1 hidden table |
| TM-12 | Location pick-heatmap | LocCode logged at pick | Free |
| TM-13 | SC spaghetti SVG | Sequence of LocCodes → polyline | Daily bot job |
| TM-14 | Pre/post baseline | 30 manually-timed issuances vs auto | 1 day of Calo |

How this maps to motion studies you'd recognise: TM-12 + TM-13 produce the Gilbreth / Frank-and-Lillian spaghetti & heatmap output. TM-10 builds an MTM-style (Methods-Time-Measurement) personal time library Calo can hand to a backup. TM-14 is the A/B baseline. TM-11 captures catalog UX friction the way modern product analytics does it. All without buying a single piece of new software, all without giving workers anything to fill in.

Other automation opportunities beyond time studies:

Watchdog bot on EResource_Updated flag — SMS to Calo if any ticket stays unsynced > 5 min.

Low-stock alert auto-creates a draft Purchase Requisition email (does not send) for SC to review and send.

Repeat-trip alert (TM-08) auto-posts in a Calo-only feed for weekly coaching review.

Returns photo-evidence flow above an AED threshold (fraud control).

Monthly stock-count CSV export auto-emailed to SC on the 1st.

Step 19 — Implementation plan (Kotter 8 × ADKAR × Tracker)

Full table in ImplementationPlan sheet. Critical near-term moves, in order:

Week 0 (now) — Force Q1 (ERP integration) decision meeting. Sponsor: Vincent. Block 60 min with IT + DX. Output: signed integration approach (API preferred). Unblocks the entire DX build clock.

Week 0 — Provision backup-SC role definition (does not need to be staffed yet, just defined in writing).

Week 1 — Inspector calibration day (Calo + Thakur on same 5 assets) BEFORE Phase B PDIs accumulate further bias.

Weeks 1–2 — Batch photography session (1 day = 100 items, not 3–5/day) to de-risk Phase D running parallel.

Weeks 2–10 — DX build runs in parallel with Phase C catalog. Two-person verify every item code before import.

Week 10 — UAT scripted by Calo (not DX). Add: stress test at 100 req/day; ERP-sync-failure-watchdog test; offline-queue test on patchy signal; sync-failure SMS escalation test.

Week 11 — Phase F final stock take + the 30 manually-timed issuances (TM-14 baseline).

Week 12 — Go-live + 2-week parallel run.

Week 14 — Hard-stop ceremony: SC's ERP write access removed; manual batch dead. Backup-SC covers 1 shift in parallel before ceremony.

Week 16 — 30-day review. Refresh defect→category map, KPI scorecard, FMEA RPNs.

Step 20 — Measurement system / control plan

Full table in ControlPlan sheet. Cadence summary:

Daily — request queue, ERP sync flag, KPI dashboard scan.

Weekly — KPI scorecard review; RCA of P95 outlier requests; low-stock-alert audit; returns spot-audit; Friday 'wins' message.

Monthly — full stock count; KPI vs target review; FMEA review.

Quarterly — catalog hygiene; SOP review.

Annual — control plan review; capacity model refresh.

Step 21 · Executive summary (A3 condensed)

A printable one-pager version is in Workshop_Stock_Exec_OnePager.docx. Inline condensation:

Background

500+ asset rental fleet; workshop store currently has no transactional record, no worker-facing tooling, and a 30–45 min nightly manual ERP batch. A 10–12 wk AppSheet build (DX Team) is planned. Pre-launch programme (Phases A–F) is in flight.

Current condition

100% of issues unrecorded · 0% ERP automation · 0% low-stock prevention · single Stock Controller (Calo) on critical path · ERP integration approach unresolved.

Target condition (by go-live + 14 days)

100% issues logged · ≥99.5% ERP sync · 100% reorder alerts pre-stockout · ≤30 min median cycle time · 1 cross-trained backup-SC active · embedded 14-point time-and-motion telemetry running.

Analysis (root causes)

RC-1 no closed-loop transaction system · RC-2 worker↔ERP UX gap · RC-3 single SC bottleneck.

Countermeasures (top 5 by Decision-matrix score)

R1 — Force Q1 (ERP integration) decision before DX build starts. (Owner: Vincent + Calo + IT + DX.)

R3 — Embed 14-point time-and-motion telemetry in the AppSheet build. (Owner: DX + Calo.)

R4 — Two-person verify on every catalog item code before import. (Owner: Calo + Thakur.)

R14 — Lock category → ERP section mapping (Buggy / SS Workshop). (Owner: Calo + IT.)

R2 — Provision backup-SC role + cross-train 1 person. (Owner: Calo + Ops Lead.)

Plan (Kotter 8 mapped to milestone tracker)

See §Steps 18–20 above. Critical Week 0 act: Q1 decision meeting.

Follow-up (measurement)

Operational scorecard sheet updated daily/weekly; FMEA + capacity model reviewed monthly; 30-day post-launch review at Week 16 with TM-14 pre-vs-post A/B as ROI evidence.