COEEx OS - Full System Diagnosis

Six-initiative portfolio - Calo, Al Laith Site Services - 10 June 2026

Companion data: Portfolio Decision Pack.xlsx + Stocktake Action Pack.xlsx (same folder). Audience: personal working plan.

# The one-page brief

Verdict: you do not have six competing projects. You have one job with a hard deadline (workshop stock control, 3 months), two dated commitments (hire desk true-up ~1 month soft, robotics showcase ~1 month), one quick win that is mostly done (staircase), and two proposals that should be sequenced behind the first win (speakers, then linkables). The mistake to avoid is doing the hire-desk work yourself for 24 days - delegate the PDI sprint to the 3 technicians and you get the same result in ~8 working days of their time plus your QC.

| Priority | Initiative | Deadline | Your hours | Exit |
| --- | --- | --- | --- | --- |
| 1 | Workshop stock control (MAIN JOB) | HARD - ~10 Sep | ~6h/wk | App live + manual interim ran clean |
| 2 | Hire desk / Season Stock true-up | Soft - ~10 Jul | ~4h/wk, techs do PDIs | Joint signed baseline + movement SOP |
| 3 | Robotics showcase | Soft - mid Jul | ~5h/wk to event | Clean demo + fallback video |
| 4 | Staircase proposal | None - take W9 | ~3h/wk | 3+ quotes, proposal tabled ~6-12 Aug |
| 5 | Speaker rental proposal | None | W9-11 | Tabled ~20-26 Aug |
| 6 | Linkable redesign | None | W11-12 | 1-page concept into capex cycle |

This week (W1): DX meeting to start the AppSheet build clock; manual interim Option A live; walk the 62 Verify-First exceptions with a hire-desk rep; resolve duplicate 188; lock showcase date; brief the designer on the staircase.

# 1. Observations (gemba)

Yard register: 697 units; 159 PDIs filed since you implemented them; the audit isolated the OPO.L gap to 34 specific rows (29 with no location recorded + 5 conflicts), duplicate sticker 188, two DA.PL portaloos excluded from the 106 count, and one orphan PDI (SSC.40.3).

Hire desk: feels the yard numbers are wrong (informal grumbling, no escalation). They are partially right - 21 units have PDIs proving presence while the register says not-in-yard. Nothing updates Season Stock because updates were defined as "unit changes", and movements are not unit changes.

Workshop: physical clean-up done; PRD v1.1, SOPs v1.0, Process v1.2 written; milestone tracker shows app build 10-12 wks - exactly your 3-month window, so the DX clock must start immediately.

Staircase: brief, Blender model and animation exist; remaining: final technical design, parts list, RFQ, proposal. Your fastest revenue story.

Speakers: April 2026 competitive analysis is genuinely strong (market sizing, BOMs, no-clone strategy, breakeven). It is a proposal-conversion task, not a research task.

Linkables: concept stage only; the crane-vs-forklift logic is compelling but it is a capex-cycle conversation.

Robotics: working JetArm, CTO co-sponsor, ExCo/ManCo audience in ~1 month. Highest personal-visibility event on your calendar.

# 2. Objective (SMART)

By 9 September 2026: workshop stock control live (hard deadline met); yard register and Season Stock reconciled and jointly signed by 8 July with a movement-update SOP holding >=98% cycle-count accuracy; robotics showcase delivered by mid-July; staircase proposal with 3+ fabricator quotes tabled by 12 August; speaker proposal tabled by 26 August; linkable concept paper submitted for the next capex cycle - all within 12h/week on side initiatives, BAU protected.

# 3. Data baseline

Full baseline in Portfolio Decision Pack.xlsx - Baseline Data; yard detail in Stocktake Action Pack.xlsx. Headlines: 109 in-yard units missing PDI; 62 exceptions to verify; OPO.L reconciliation band 113-118 vs your count of 115; workshop parts spend assumption 250k AED/yr; speaker build cost 2,500-8,500 AED vs 25,000-33,000 AED retail equivalents; staircase modelled at 1,200 AED/unit build, 150 AED/wk rental (assumptions marked yellow in the pack - confirm before quoting upward).

# 4. Constraint analysis (TOC)

The system constraint is your hours and your credibility pipeline - every initiative routes through you. Exploit: spend your hours only where you are the unique resource (DX negotiation, hire-desk sign-off, proposals, showcase). Subordinate: PDIs, portaloo line-up, catalog photography go to technicians and the stock controller. Elevate: the AppSheet automation removes you from the workshop loop permanently; the movement SOP removes you from the Season Stock loop. Secondary constraint: the single design resource (staircase) - brief them in W2 so their clock runs parallel to yours. Tertiary: exec attention - one proposal at a time, staircase first because it is nearly done and cheap to say yes to.

# 5. Process map - the data integrity chain (VSM)

Physical yard -> PDI app -> Maintenance overview -> Season Stock -> hire desk quoting. Information dies at three points: (1) movements (KSA, sites, hotel) never write back to the register; (2) portaloos cannot be verified because stickers are hidden; (3) returns re-enter the yard without a record. The fix is not more counting - it is event-driven updates: every Delivery Note and Return Note triggers a same-day register update, mirroring exactly the input-based integration principle in your own web-app PRD. Current-state and future-state maps: see the visual in chat (Figma substitute).

# 6. Waste audit (TIMWOODS)

| Waste | Where it shows up | Severity |
| --- | --- | --- |
| Defects | 62 wrong/conflicting register rows; duplicate 188; orphan SSC.40.3 | HIGH - drives all distrust |
| Overprocessing | Same unit status maintained in 3 places by hand (register, maintenance overview, Season Stock) | HIGH |
| Waiting | Hire desk re-verifies before quoting; quotes delayed; DX queue idle until PRD meeting | MED |
| Inventory | 109 unknown units = frozen rentable capital; untracked workshop parts | MED |
| Motion | Searching for units; portaloo stack hides stickers | MED |
| Transport | One-off portaloo rearrangement (necessary, one time) | LOW |
| Overproduction | Re-counting already-confirmed units (avoid: verify by exception) | LOW |
| Skills | You doing technician-level PDIs; workers expected to touch ERP (your PRD already fixes this) | HIGH for your hours |

Pareto: defects + overprocessing account for most of the trust damage; skills-waste accounts for most of your lost hours. Fix those three and the rest shrinks.

# 7. Bottleneck

Short term: physical verification capacity. 109 PDIs at ~5 PDIs/tech/day with 3 technicians = ~7-8 working days - inside your 1-month soft deadline with margin, IF delegated (your 24-day solo estimate is the cost of not delegating). Medium term: the DX build queue (10-12 wks) is the workshop critical path; every week the PRD meeting slips, go-live slips a week. Nothing else in the portfolio is capacity-bound; items 4-6 are decision-bound.

# 8. Root cause (5 Whys + fishbone)

Hire desk feels the numbers are wrong - why?

Season Stock has not been updated in months - why?

The update rule is "update when units change", and no units changed - why is that the rule?

Movements (dispatch, return, KSA transfer) were never classified as register events - why?

No owner or trigger was ever assigned for movement data: DNs/RNs do not write back. ROOT CAUSE.

Verification: the audit proves it - 21 units with PDIs marked absent, 29 no-location rows, portaloo flags 23/85 inverted vs a physical count of 102. Fishbone: Methods (no movement SOP) and Systems (3 disconnected sheets) dominate; People (single-point-of-failure: you), Materials (missing stickers), Measurement (no cycle counts), Environment (off-site units invisible).

# 9. Human factors

You: hero-mode risk. The 24-days-solo instinct is the failure mode, not the plan. Your value is in designing systems others run.

Hire desk: needs to co-own the number. Bring their rep on the W1 walk and have them sign the true-up - it becomes "our baseline", and the grumbling converts into advocacy.

Technicians: PDIs are respectful, skilled work with a clear checklist - delegation here is development, not dumping.

Stock controller: the manual interim makes their remote-work need real from day 1.

CTO: an ExCo-level sponsor attached to your name. Protect the showcase date.

Manager: receives one clean proposal at a time, each with quotes and margins - never a pile of ideas.

# 10. Economics (T / OE / I)

Full model with editable assumptions: Portfolio Decision Pack.xlsx - Economics T-OE-I and the dedicated Staircase Model sheet. Headlines: stocktake true-up costs ~0 and re-activates up to 29 suspect linkables (every recovered unit rents at ~2,500 AED/mo); workshop control pays back in ~2-3 months on shrinkage alone at 4% of a 250k parts spend. Staircase is SAVINGS-LED at 250 units: wooden maintenance (wood, paint, astroturf) plus the dedicated-truck problem (5/truck, separate vehicle) versus fold-flat metal that rides between cabins (~50/truck standalone) - savings alone repay the fleet capex in months, with rental (20-60% utilisation, week vs day pricing unresolved) and standalone sales as upside, not as the case. Speakers model ~140% annual rental yield on phase-1 capex per the April analysis; linkables save ~3,500 AED of crane mobilisation per replaced move. Decision-tree logic: bank the free wins first (1-2), use the showcase for visibility (3), then spend credibility on capex asks in ascending size (4 then 5 then 6).

# 11. Top risks (FMEA)

Register: Portfolio Decision Pack.xlsx - Risk FMEA (10 modes, RPN-ranked). Top five:

Staircase certification overlooked: spec load rating / EN 12811 into the RFQ itself.

Season Stock drifts back after true-up: movement SOP + monthly cycle count, owner = yard supervisor.

Overcommitment erodes BAU: 12h/wk cap; drop lowest-rank initiative if breached 2 weeks running.

Showcase demo fails live: two rehearsals + pre-recorded fallback.

DX slips the 10-12wk build: manual interim absorbs the gap; escalate at the W6-7 checkpoint.

# 12. Automation roadmap

Now (manual interim): issuance log sheet + weekend procedure (already designed in PRD section 18).

Workshop app (W1-W12): e-resource automation agent per PRD section 10 - zero worker ERP contact.

Register: DN/RN-triggered Season Stock update - manual SOP now, becomes automatic when the webapp Fleet Dashboard engine lands (input-based integration, DO #4/#8 in your build rules).

PDI -> register: weekly export comparing PDI folder names vs in-yard flags (the exact cross-check used in this diagnosis - scriptable).

Quote-blocking on plant numbers (webapp DO #18) ends double-booking risk permanently.

# 13. Implementation plan (Kotter / ADKAR)

Week-by-week plan with owners and hours: Portfolio Decision Pack.xlsx - 90-Day Plan. Change anchors: Urgency = hire-desk doubt + 3-month deadline (real, dated). Coalition = hire-desk rep + yard supervisor + stock controller + CTO. Quick win = signed true-up by 8 July, published. Anchor = movement SOP + cycle-count cadence so the fix survives you. ADKAR for the movement SOP: Awareness (show the 62-row evidence), Desire (fewer re-checks before quoting), Knowledge (one-page SOP), Ability (W2-W4 supervised practice), Reinforcement (cycle-count results shared monthly).

# 14. Measurement system

Control plan: Portfolio Decision Pack.xlsx - Scorecard Control Plan. Nine KPIs with targets, owners, red-triggers: register accuracy >=98%, sync lag <=2 days, PDI coverage >=95% by 9 Sep, exceptions 62->0 by 30 Jun, 100% issuance logging, shrinkage <1%/mo, 3+ staircase quotes by 5 Aug, 2 clean showcase rehearsals, side-hours <=12/wk. Review: 30 minutes every Friday against the scorecard; monthly cycle count; update the pack after each milestone.

# 15. Your three questions, answered

## 1. Keep my job and show the most progress

Workshop (it IS the job, and it has the only hard deadline) + the hire-desk true-up (it is the only place someone currently doubts you - kill that narrative within a month, jointly signed). Both are execution of work you have already designed - maximum progress per hour.

## 2. Launch order, feasibility and completeness

Workshop interim W1 (100% designed) -> hire-desk baseline by W4 (80% done via audit) -> robotics showcase W5 (65%, date-fixed) -> staircase proposal W9 (35% overall but short path remaining) -> speaker proposal W11 (45% done on paper, needs exec appetite) -> linkable concept W11-12 (10%, capex-cycle item).

## 3. What makes ME the most money

Sequence, not selection. The raise case writes itself in this order: removed the one doubt about my area (true-up, signed by hire desk) -> delivered my main project on a hard deadline (workshop) -> showed ExCo something memorable with the CTO vouching (showcase) -> then asked for money with a cheap, quoted, revenue-generating prototype (staircase) -> then the bigger swing (speakers) while it is warm. The staircase is your first AED-attribution; the speaker proposal is the biggest upside narrative; the linkable paper marks you as fleet-strategy material. A raise conversation in September has five receipts behind it.

# 16. Maintenance plan

Friday 30-min self-review vs scorecard (owner: you). Monthly: cycle count + share results with hire desk. After each milestone: update 90-Day Plan status column and FMEA occurrences. Quarter-end: rerun this diagnosis lite (constraint moved? re-rank the matrix).