## README
AL LAITH SITE SERVICES - PORTFOLIO DECISION PACK
Companion to: COEEx Full System Diagnosis.docx (same folder). Linked: Stocktake Action Pack.xlsx (yard detail).
Blue cells = editable inputs. Yellow = assumptions to confirm. Built 10 Jun 2026.

## Baseline Data
Initiative | Current status (observed 10 Jun 2026) | Key evidence / source | Readiness %
1. Yard stocktake + register true-up | Audit done: 697 units, 159 PDIs filed, 62 verify-first exceptions, 109 in-yard units missing PDI, OPO.L gap isolated to 34 rows, duplicate sticker 188 found | Stocktake Action Pack.xlsx; UAE Inventory Audit.xlsx; PDI Drive folder | 80
2. Hire desk / Season Stock accuracy | Hire desk distrusts yard numbers. Root cause proven: register flags stale on MOVEMENTS (21 provably wrong flags, 29 no-location units) - not on unit changes | Audit cross-ref vs PDIs; chain: PDI app - Maintenance overview - Season Stock | 60
3. Workshop stock control | PRD v1.1 ready for DX review (AppSheet, app f65652e0); SOPs v1.0 + Process v1.2 written; manual interim Options A/B designed; milestone tracker: phases A-F + 10-12wk app build | workshop problem folder, 4 documents | 70
4. Metal modular staircase | Brief + coating research done; Blender model + configuration animation done; needs: engineering drawings, parts list, RFQ to fabricators (1 vs 100 units), proposal | Staircase idea folder: brief docx, showcase.mp4, staircase_full.blend | 35
5. Speaker rental entry | Full competitive analysis complete (Apr 2026): MICE market $6.14B-$11B 2032; build cost 2,500-8,500 AED vs 25,000-33,000 AED retail equivalents; no-clone strategy defined | Speaker idea folder: competitive analysis docx | 45
6. Linkable cabin modular redesign | Concept only: replace crane-dependent ablutions with forklift-only modular linkables. No drawings, no costings yet | Stated intent; fleet data in maintenance workbook | 10
7. Robotics showcase (with CTO) | Hiwonder JetArm working, big progress; vision training remaining; ExCo+ManCo showcase scheduled [ASSUMPTION: ~mid-Jul] | Side project with CTO sponsorship | 65

## Decision Matrix
Criterion weights (edit blue): | Job security | Time-to-value | Feasibility | Business leverage | Personal ROI
Weight | 0.3 | 0.2 | 0.2 | 0.2 | 0.1
Initiative | Job security (1-5) | Time-to-value (1-5) | Feasibility (1-5) | Business leverage (1-5) | Personal ROI (1-5) | Weighted score | Rank
1. Stocktake close-out + Season Stock true-up (1-mo soft deadline, delegate to 3 techs) | 4 | 5 | 5 | 4 | 4 | 4.4 | 2
2. Workshop stock control - MAIN JOB, 3-month hard deadline | 5 | 4 | 5 | 4 | 4 | 4.5 | 1
3. Robotics showcase (CTO soft deadline ~1 month) | 3 | 4 | 4 | 2 | 5 | 3.4 | 4
4. Staircase - quick win, majorly done (design+quotes left) | 3 | 4 | 4 | 5 | 5 | 4 | 3
5. Speaker rental proposal | 2 | 2 | 3 | 5 | 4 | 3 | 5
6. Linkable redesign concept paper | 2 | 1 | 2 | 5 | 3 | 2.5 | 6
Lens views: rank by column B = keep your job; by C+D = launch order; by F = personal money. Weighted = balanced answer.
Intake 10 Jun: capacity 12h/wk for items 3-6; workshop is BAU main job; hire desk = informal grumbling.
Staircase reframed 10 Jun (PM): savings-led case - 250 fleet, piggyback transport, sale SKU. Sequence unchanged (deadlines rule W1-W5); proposal still lands W9.

## Economics T-OE-I
Initiative | Investment I (AED) | Annual T potential (AED) | OE delta (AED/yr) | Payback (months) | Basis / assumptions (yellow = edit me)
Stocktake true-up | 0 | 261000 | 0 | 0 | 29 suspect OPO.L returned to rentable pool; 2,500 AED/mo rate x 30% utilisation uplift [ASSUMPTION]
Workshop control | 2000 | 10000 | 0 | 2.4 | Parts spend 250,000 AED/yr [ASSUMPTION]; shrinkage stopped 4%; I = labels/cage
Staircase (250 units, savings-led) | 300000 | 525500 | 12500 | 26.5683 | SAVINGS-LED: maintenance + transport savings are firm; rental at 20% util WEEK pricing as conservative upside. Full model: Staircase Model sheet
Speaker rental (phase 1 rig) | 120000 | 168000 | 35000 | 10.8271 | Phase-1 inventory 120k AED (subs+tops per analysis); rental yield 140%/yr of capex in MICE [ASSUMPTION]; OE = tech+transport
Linkable redesign (pilot 5) | 225000 | 126000 | 10000 | 23.2759 | Pilot 5 units at 45k; saves crane mob 3,500 AED x 60 moves/yr x 60% replaced [ASSUMPTION]
Robotics showcase | 0 | 0 | 0 |  | Strategic/visibility value - not cash-modelled

## Risk FMEA
# | Failure mode | Effect | S | O | D | RPN | Mitigation | Owner
1 | Stocktake stalls; suspects unresolved | Hire desk distrust hardens; job-security risk | 8 | 4 | 3 | 96 | Verify-First list already built; book half-day this week with hire-desk rep present | Calo
2 | Hire desk escalates before true-up lands | Narrative set by others, not by data | 7 | 3 | 2 | 42 | Share 62-item findings NOW as interim proof of grip; joint sign-off of trued-up Season Stock | Calo + Hire desk lead
3 | Duplicate 188 mis-assigned | Register corrupted twice; audit credibility hit | 6 | 3 | 4 | 72 | PDI-photo match protocol; if unprovable assign OPO.L.20.204 | Calo
4 | DX team delays AppSheet build (10-12 wks) | Workshop control gap persists | 6 | 6 | 2 | 72 | Manual interim Option A live now; monthly stock-take bridge (Option B) as fallback | Calo + DX
5 | Showcase live demo fails | Visibility moment wasted in front of ExCo | 8 | 4 | 3 | 96 | Scripted demo path; pre-recorded fallback video; rehearse twice | Calo + CTO
6 | Design resource unavailable for staircase | Proposal slips past budget window | 5 | 5 | 3 | 75 | Issue RFQ on concept drawings + parts list from Blender model; refine after | Calo + Design
7 | Staircase certification (load/HSE) overlooked | Product unusable on event sites | 9 | 3 | 5 | 135 | Spec EN 12811/load rating into RFQ; ask fabricators for certified design | Design
8 | Speaker plan framed as cloning IP | Legal/brand risk; exec rejection | 7 | 3 | 4 | 84 | Follow no-clone strategy in analysis: cardioid subs + mid-market arrays, own branding | Calo
9 | Overcommitment; BAU quality slips | The 18 PRD items + stocktake suffer = job risk | 8 | 5 | 3 | 120 | 8h/wk cap on side initiatives; sequence proposals one at a time | Calo
10 | Season Stock updated but process not changed | Drift returns in 3 months | 7 | 5 | 4 | 140 | Movement-trigger SOP: every DN/RN updates register same day; monthly cycle count | Yard supervisor

## 90-Day Plan
Week | Dates | Initiative | Action | Owner | Hours | Milestone / exit criteria | Status
W1 | 11-17 Jun | Workshop (MAIN) | PRD v1.1 review meeting with DX THIS WEEK - the 10-12wk app build must start now to fit the 3-month deadline | Calo + DX | 3 | DX build clock started
W1 | 11-17 Jun | Workshop (MAIN) | Manual interim Option A go-live: issuance log, weekend procedure, e-resource cadence | Calo + Stock controller | 4 | Issuances logged from day 1
W1 | 11-17 Jun | Hire desk | Walk the 62 Verify-First exceptions with one hire-desk rep; resolve duplicate 188 via PDI photos | Calo + hire desk rep | 5 | 62 list closed; 188 resolved
W1 | 11-17 Jun | Robotics | Lock showcase date + demo script with CTO | Calo + CTO | 2 | Date + script agreed
W2 | 18-24 Jun | Hire desk | Portaloo line-up + sticker check (DA.PL.57/58); START delegated PDI sprint: 3 technicians x ~5 PDIs/day | 3 techs + Calo QC | 6 | Backlog 109 -> ~60
W2 | 18-24 Jun | Staircase | Hand designer the blend+brief; agree final technical design scope + load spec | Calo + Design | 3 | Design started
W2 | 18-24 Jun | Workshop (MAIN) | Phases C/D from milestone tracker: catalog + photography continue alongside app build | Stock controller | 3 | Catalog moving
W3 | 25 Jun-1 Jul | Hire desk | PDI sprint week 2 (techs continue); Calo spot-QCs 10% | 3 techs | 4 | Backlog -> ~20
W3 | 25 Jun-1 Jul | Robotics | Vision training x3 sessions; rehearsal 1; record fallback video | Calo + CTO | 6 | Clean scripted run
W4 | 2-8 Jul | Hire desk | Backlog done; Season Stock TRUE-UP + joint sign-off with hire desk; movement-update SOP agreed (every DN/RN updates sheet same day) | Calo + Hire desk lead | 4 | SIGNED baseline inside 1-mo deadline
W4 | 2-8 Jul | Robotics | Rehearsal 2 + contingency check | Calo + CTO | 4 | Demo locked
W5 | 9-15 Jul | Robotics | SHOWCASE to ExCo + ManCo (CTO soft deadline) | Calo + CTO | 6 | Delivered; follow-ups captured
W5 | 9-15 Jul | Staircase | Final design + parts list done; RFQ out to 3+ fabricators, qty 1 AND qty 100 | Design + Calo | 4 | 3+ RFQs issued
W6-7 | 16-29 Jul | Workshop (MAIN) | App build mid-checkpoint vs PRD; test data model + e-resource automation agent | Calo + DX | 4 | On schedule
W6-7 | 16-29 Jul | Hire desk | Monthly cycle count #1 (20 random units) - prove accuracy holds | Calo | 2 | >=98% match
W8 | 30 Jul-5 Aug | Staircase | Quotes back; comparison matrix; proposal pack (prototype + 100-unit pricing, wooden replacement case) | Calo | 5 | Proposal ready
W9 | 6-12 Aug | Staircase | PROPOSAL TO MANAGER - your first revenue win | Calo + Manager | 2 | Prototype PO / decision
W9-10 | 6-19 Aug | Speaker | Convert Apr analysis into 3-page exec proposal: phase-1 rig, roster clients, breakeven | Calo | 6 | Draft ready
W11 | 20-26 Aug | Speaker | Table speaker proposal (riding staircase credibility) | Calo + Manager | 2 | Decision requested
W11-12 | 20 Aug-2 Sep | Linkable | 1-page concept + crane-vs-forklift cost data collection | Calo | 4 | Concept for capex cycle
W12-13 | 27 Aug-9 Sep | Workshop (MAIN) | App UAT -> go-live + monitoring; manual-to-app transition per PRD section 18.7 - 3-MONTH DEADLINE MET | Calo + DX + Stock controller | 6 | LIVE
W13 | 3-9 Sep | All | 90-day review vs scorecard; cycle count #3; next-quarter plan | Calo | 2 | Scorecard green
Capacity check: side-initiative rows (Robotics/Staircase/Speaker/Linkable) never exceed 12h in any week; PDI sprint is delegated to technicians (your 24-day solo estimate becomes ~8 working days of tech time + your QC).

## Scorecard Control Plan
KPI | Definition | Target | Cadence | Owner | Data source | Red trigger -> reaction
Register accuracy | Cycle-count sample match vs register | >=98% | Monthly (20 random units) | Calo | Stocktake Action Pack | <95% -> root cause within 1 wk
Season Stock sync lag | Days between physical movement and sheet update | <=2 days | Weekly spot check | Hire desk lead | DN/RN log vs sheet | >5 days -> escalate SOP breach
PDI coverage | % of in-yard fleet with PDI on file | >=95% by 9 Sep | Weekly | Calo | PDI Drive folder count | Stalls 2 wks -> reassign hours
Verify-First exceptions open | Of the 62 flagged units | 0 by 30 Jun | Weekly | Calo | Action Pack Verify sheet | >10 on 30 Jun -> extend walk
Parts issuance logged | % workshop issues with log entry | 100% | Weekly | Stock controller | Manual log / AppSheet | Any unlogged -> retrain + lock store
Parts shrinkage | Unexplained stock variance | <1%/mo | Monthly count | Stock controller | e-resource vs physical | >2% -> access review
Staircase pipeline | RFQs received | >=3 quotes by 5 Aug | Biweekly | Calo | RFQ tracker | <2 -> widen fabricator list
Showcase readiness | Scripted demo pass rate | 2 clean rehearsals | Before event | Calo + CTO | Rehearsal log | Fail -> default to video
Side-initiative hours | Hours/wk on items 3-6 | <=12h/wk | Weekly | Calo | Self-track | >14h 2wks running -> drop lowest rank

## Staircase Model
STAIRCASE: SAVINGS-LED BUSINESS CASE (edit blue inputs; yellow = pull from actuals)
INPUTS
Fleet size at full rollout (you said 200-300) | 250
Build cost per metal unit (pending RFQ) | 1200 | AED - confirm with quotes
Wooden maintenance per unit per yr (wood+paint+astroturf) | 400 | AED - PULL FROM WORKSHOP ACTUALS
Metal maintenance per unit per yr | 50 | AED - coating touch-up only
Staircase unit-movements per yr | 400 | PULL FROM DELIVERY NOTES
Wooden: units per truck | 5 | and it is a SEPARATE truck
Truck trip cost | 600 | AED - PULL FROM LOGISTICS ACTUALS
Metal: rides between cabins on same truck | 1 | 1=yes (0 dedicated trips for bundled moves)
Metal: units per truck when standalone | 50 | flat-folded
Standalone rental rate - WEEK scenario | 150 | AED/wk
Standalone rental rate - DAY scenario | 150 | AED/day (events only)
Sale price per unit (new standalone product) | 2500 | AED
Units sold per yr | 20 | conservative
SAVINGS (the firm part of the case)
Maintenance saving per yr | 87500 | fleet x (wood - metal)
Transport: wooden dedicated trips per yr | 80
Transport: metal dedicated trips per yr | 0 | rides with cabins
Transport saving per yr | 48000
TOTAL ANNUAL SAVING | 135500
Capex (full fleet) | 300000
Payback from savings alone (months) | 26.5683
REVENUE UPSIDE (the speculative part - price point unresolved)
Utilisation scenario | 20% | 40%¦60% grid below
Annual rental revenue grid (fleet x util x rate) | WEEK pricing (x52) | DAY pricing (x365)
Utilisation 20% | 390000 | 2737500
Utilisation 40% | 780000 | 5475000
Utilisation 60% | 1170000 | 8212500
Sales margin per yr | 26000
PROPOSAL FRAMING
Lead with savings: maintenance + transport pay for the fleet in ~B25 months with zero demand risk.
Rental + sales are upside, not the case. Day-rate applies to event walkway/bridge/ramp configs only.
Wooden standalone rental today ~1%/yr - the modular configs (walkway, bridge, ramp, ladder, shelf) create NEW standalone demand that wood cannot serve.