## Milestone Tracker
AL LAITH SITE SERVICES
Workshop Stock Control — Milestone Tracker
Status: Pending = blank ¦ In Progress = type "►" ¦ Done = type "✓" Last updated: ___________
PROGRAMME OVERVIEW
Phase A | Asset Clearout | 1–2 wks |  | Start: Immediately
Phase B | Yard Assessment | 2–3 wks |  | Start: Immediately (with A)
Phase C | Catalog Documentation | 1–2 wks |  | Start: After A complete
Phase D | Photography | 1 wk |  | Start: Alongside C
Phase E | e-Resource Alignment | 2–3 wks |  | Start: After C begins
Phase F | Final Stock Take | 1 wk |  | Start: After A–E done
Labeling | Physical Setup | 1–2 wks |  | Start: After C + D done
App Build | Soluchan builds AppSheet | 10–12 wks |  | Start: Immediately (parallel A–B)
Launch | Go-Live & Monitoring | 2+ wks |  | Start: After all phases complete
# | Phase | Milestone / Task | Owner | Target | Status | Date Done | Notes
PRE-LAUNCH PREPARATION PROGRAMME
PHASE A · Asset Clearout — Recover Workshop Items from All Assets [1–2 weeks — Start: Immediately]
1 | PHASE A | Print full asset list, plan clearout route for the yard | Calo | Week 1
2 | PHASE A | Clear all cabins (DRS / OPO) — remove every workshop item found | Calo + Team | Week 1
3 | PHASE A | Clear all ablution units | Calo + Team | Week 1
4 | PHASE A | Clear all buggies and vehicles | Calo + Team | Week 1
5 | PHASE A | Clear flatpacks, flexiloos, portaloos, messhalls | Calo + Team | Week 1–2
6 | PHASE A | Consolidate all recovered items in workshop | Calo + Team | Week 2
7 | PHASE A | Categorise and rough-sort recovered items on arrival | Calo | Week 2
PHASE B · Yard Maintenance Assessment — Rental Readiness & Parts Demand [2–3 weeks — Start: Immediately (with A)]
8 | PHASE B | Open SS Inspections app, systematically inspect every asset | Calo / Inspector | Week 1–3
9 | PHASE B | Record all defects, parts needed, tools needed per asset | Calo / Inspector | Week 1–3
10 | PHASE B | Complete Phase B tracker — all columns filled for every asset | Calo | Week 3
11 | PHASE B | Assign rental readiness status to every asset | Calo | Week 3
12 | PHASE B | Prioritise assets: booked first → minor works → maintenance → not rentable | Calo | Week 3
13 | PHASE B | Flag any unaccounted or missing assets to management | Calo | Week 3
PHASE C · Parts Catalog Documentation — Exact Names, Specs & Item Codes [1–2 weeks — Start: After Phase A complete]
14 | PHASE C | Handle each physical item — identify exact manufacturer name and spec | Calo | Week 3–4
15 | PHASE C | Search e-resource for official item code for each item | Calo | Week 3–4
16 | PHASE C | Assign internal code (e.g. PL-001) for items not yet in e-resource | Calo | Week 3–4
17 | PHASE C | Complete all catalog spreadsheet columns for every item | Calo | Week 4
18 | PHASE C | Identify parts gap — Phase B demand items not currently in stock | Calo | Week 4
19 | PHASE C | Set reorder thresholds for every stocked item | Calo | Week 4
20 | PHASE C | Catalog spreadsheet confirmed complete and ready for app import | Calo | Week 5
PHASE D · Parts Photography — Catalog Images for the App [1 week — Start: Run alongside Phase C]
21 | PHASE D | Set up photo area: white background, bright even lighting | Calo | Week 3
22 | PHASE D | Photograph every inventory item (min 800×800px, part fills 60% of frame) | Calo | Week 3–4
23 | PHASE D | Photograph all workshop tools | Calo | Week 4
24 | PHASE D | Name all files correctly: [Part_Number]_[short_name].jpg | Calo | Week 4
25 | PHASE D | Create Google Drive folder: Workshop Stock > Part Images | Calo | Week 3
26 | PHASE D | Upload all photos; record filename in catalog Photo_Filename column | Calo | Week 4–5
27 | PHASE D | Share Part Images folder link with Soluchan for app import | Calo | Week 5
PHASE E · e-Resource Alignment — Integration, Sections & Book Accuracy [2–3 weeks — Start: After Phase C begins]
28 | PHASE E | E.1 — Ask IT: does any existing system auto-update e-resource? | Calo | Week 3
29 | PHASE E | E.1 — Document the integration method; share with Soluchan | Calo / IT | Week 4
30 | PHASE E | E.2 — Confirm "Buggy Parts" section exists separately in e-resource | Calo / IT | Week 3–4
31 | PHASE E | E.2 — Confirm "SS Workshop Store" section exists separately in e-resource | Calo / IT | Week 3–4
32 | PHASE E | E.2 — Confirm issuing from one section does not affect the other | Calo / IT | Week 4
33 | PHASE E | E.3 — Export current e-resource inventory list for both sections | Calo / IT | Week 4
34 | PHASE E | E.3 — Compare vs Phase C catalog; flag all discrepancies | Calo | Week 5
35 | PHASE E | E.3 — Clean records with IT: remove phantoms, zero wrong quantities | Calo / IT | Week 5
36 | PHASE E | E.3 — IT confirms records are ready for Phase F final counts | IT | Week 5–6
37 | PHASE E | E.4 — Meet Soluchan: confirm he has all integration details needed | Calo + Soluchan | Week 6
38 | PHASE E | E.4 — Agree on test procedure: 5+ end-to-end issuances before go-live | Calo + Soluchan | Week 6
PHASE F · Final Pre-Launch Stock Take — Workshop, Yard & Misc Items [1 week — Start: After Phases A–E complete]
39 | PHASE F | F.1 — Count every workshop item physically against catalog | Calo | Week 11
40 | PHASE F | F.1 — Load all opening stock quantities into app and e-resource | Calo / Soluchan | Week 11
41 | PHASE F | F.2 — Confirm every fleet asset is physically present or accounted for | Calo | Week 9–10
42 | PHASE F | F.2 — Record physical bay/row/zone location of each yard asset | Calo | Week 9–10
43 | PHASE F | F.3 — Complete KSA vs UAE ownership column for every asset | Calo / Mgmt | Week 10
44 | PHASE F | F.3 — Flag all "To Confirm" ownership items to management; get sign-off | Calo | Week 10
45 | PHASE F | F.4 — Walk full yard perimeter; count all miscellaneous items | Calo | Week 10
46 | PHASE F | F.4 — Road cones, picnic benches, staircases: qty, condition, ownership | Calo | Week 10
LABELING & PHYSICAL SETUP
LABELING · Workshop Labeling & Google Sheet Quick Reference [1–2 weeks — Start: After Phase C + D complete (Week 5–6)]
47 | LABELING | Walk workshop; assign shelf group letters A–Z from entrance inward | Calo | Week 5–6
48 | LABELING | Print and mount shelf section header labels (A5, colour-coded per category) | Calo | Week 6
49 | LABELING | Print and apply item bin labels for all inventory items (coloured header) | Calo | Week 6–7
50 | LABELING | Print and apply consumable bin labels for all consumables (black header) | Calo | Week 6–7
51 | LABELING | Populate Google Sheet Quick Reference: all items, all 9 columns | Calo | Week 6–7
52 | LABELING | Verify FILTER search formula returns correct location results | Calo | Week 7
53 | LABELING | Share Quick Reference with team; confirm access permissions set | Calo | Week 7
APP BUILD — SOLUCHAN (10–12 WEEKS, RUNNING PARALLEL TO PHASES A & B)
APP BUILD · AppSheet App Build — Soluchan [10–12 weeks — Start: Immediately (parallel to Phases A–B)]
54 | APP BUILD | All 6 data tables built (Catalog, Inventory, Requests, Line Items, Tickets, Returns) | Soluchan | Week 2–3
55 | APP BUILD | Field Worker role: inspection-triggered request flow working end-to-end | Soluchan | Week 4–5
56 | APP BUILD | Visual catalog live: Category → Subcategory → Part + photo | Soluchan | Week 5–6
57 | APP BUILD | Stock Controller role: request queue, accept/reject, remote access | Soluchan | Week 6–7
58 | APP BUILD | Automation agent for e-resource integration built and configured | Soluchan | Week 7–9
59 | APP BUILD | Low stock alert automation active and tested | Soluchan | Week 8
60 | APP BUILD | Hindi language labels applied throughout app | Soluchan | Week 9
61 | APP BUILD | End-to-end test issuances run and passed (minimum 5) | Soluchan + Calo | Week 10–11
62 | APP BUILD | UAT session completed with Calo — all flows signed off | Calo + Soluchan | Week 11
63 | APP BUILD | Formal sign-off received: Vincent Nibbering + John Maddern | Calo | Week 12
LAUNCH & HANDOVER
GO-LIVE CHECK · Go / No-Go Checklist — All Must Be ✓ Before App Launches
64 | GO-LIVE CHECK | All workshop items counted; opening quantities loaded into app + e-resource | Calo | Week 12
65 | GO-LIVE CHECK | Every catalog entry has a confirmed e-resource item code | Calo | Week 12
66 | GO-LIVE CHECK | Every catalog entry has a part photo uploaded to app | Calo | Week 12
67 | GO-LIVE CHECK | e-resource sections confirmed separate: Buggy Parts + SS Workshop Store | Calo / IT | Week 12
68 | GO-LIVE CHECK | Automation agent tested: 5+ end-to-end issuances passed in UAT | Soluchan + Calo | Week 12
69 | GO-LIVE CHECK | All shelf + bin labels printed and applied in workshop | Calo | Week 12
70 | GO-LIVE CHECK | Google Sheet Quick Reference fully populated and shared with team | Calo | Week 12
71 | GO-LIVE CHECK | Manual interim system closed; all open requests transferred to digital | Calo | Week 12
LAUNCH · Launch & Post-Launch Monitoring [2+ weeks — Start: After Go/No-Go checklist complete]
72 | LAUNCH | Field worker briefings completed — all staff (15 min each) | Calo | Week 12
73 | LAUNCH | Stock Controller (Calo) 1-hour full app walkthrough with Soluchan | Soluchan | Week 12
74 | LAUNCH | 2-week parallel run started: manual + digital both active | Calo | Week 12–14
75 | LAUNCH | Daily request queue checks during first 2 weeks | Calo | Week 12–14
76 | LAUNCH | Manual system officially stopped — digital only from this point | Calo | Week 14
77 | LAUNCH | 30-day review: data quality, alert accuracy, process gaps assessed | Calo | Week 16
LEGEND |  | ✓ Done — row turns green | ► In Progress — row turns amber | (blank) Pending — no colour